## LaunchBlocking
Issue key | Summary | Status | Points | Assignee | Sprint | NOTES
Domain - Radiology Images Initial Experience
MHV-62899 | Add CVIX reports that do not exist in VIA to front end reducer data | Done | 3 | michael.moyer@va.gov | MHV Sprint 144 VA.gov MR | QA Comment: back end test /no test case required
MHV-64151 | Fix issues with large DICOM download | Done | 2 | michael.moyer@va.gov | MHV Sprint 145 VA.gov MR | Maruf
MHV-64150 | Update URL for imaging APIs to remove PII | Done | 3 | oleksii.morgun@va.gov | MHV Sprint 144 VA.gov MR | Maruf
MHV-64538 | Verify that CVIX reports follow proper business rules | Done | 1 | michael.moyer@va.gov | MHV Sprint 144 VA.gov MR | Maruf
MHV-44894 | Connect to MHV images and display on front end | Done | 5 | justin.lattimore@va.gov | MHV Sprint 145 VA.gov MR | Maruf
MHV-62910 | Add request images functionality to Radiology details page | Done | 3 | justin.lattimore@va.gov | MHV Sprint 145 VA.gov MR | Maruf
Download Continuity of Care Document (CCD)
MHV-62802 | Create reducer and action for CCD | Done | 3 | kolby.balch@va.gov | MHV Sprint 142 VA.gov MR | QA Comment: No QA subtask
MHV-61930 | Connect to backend to download CCD document | Done | 3 | kolby.balch@va.gov | MHV Sprint 145 VA.gov MR | QA Comment: back end test /no test case required
Download Medical Records
MHV-60263 | Clean up and add new Blue Button domains to BB PDF | Done | 5 | matthew.wright8@va.gov | MHV Sprint 137 VA.gov MR | C109076
MHV-61944 | Update the content on the MR landing page to navigate to the new download page | Done | 2 | victoria.saleem@va.gov | MHV Sprint 144 VA.gov MR | C109077
MHV-64147 | Create reducer for remaining BB download domains | Done | 3 | matthew.wright8@va.gov | MHV Sprint 143 VA.gov MR | QA Comment: No QA subtask
MHV-60285 | Clean up and add new Blue Button domains to BB txt | Done | 3 | Tywande.Barnes@va.gov | MHV Sprint 145 VA.gov MR | C109078
MHV-61927 | Select filters to download report(s) 3 steps - date range, items and file type | Done | 3 | kolby.balch@va.gov | MHV Sprint 145 VA.gov MR | C109079
Download Self Entered Health History
MHV-61932 | Connect to MHV backend for Self entered records | Done | 3 | michael.moyer@va.gov | MHV Sprint 144 VA.gov MR | QA Comment: back end test /no test case required
MHV-64662 | Add error handling for self-entered data APIs | Done | 2 | michael.moyer@va.gov | MHV Sprint 144 VA.gov MR | QA Comment: No QA subtask
MHV-64869 | Update the self entered records PDF downloads with live data | Done | 3 | matthew.wright8@va.gov | MHV Sprint 144 VA.gov MR | C109080
Prepare for Phase 1 (Launch Blocking)
MHV-64357 | Test FE in Staging alongside Muazzam for MHV-61973 | Done | 1 | michael.moyer@va.gov | MHV Sprint 144 VA.gov MR | QA Comment: back end test /no test case required
MHV-64536 | Pre Release-Priority 6: Update content and link on MR landing page | Done | 1 | victoria.saleem@va.gov | MHV Sprint 144 VA.gov MR | C109081
MHV-64616 | Pre release-Priority 5: Vitals marked "unavailable" or "refused" by providers create an error state on MHV | Done | 1 | kyle.cardwell@va.gov | MHV Sprint 144 VA.gov MR | C109082
MHV-64621 | Pre release-Priority 3: Comments on health conditions poorly formatted and confusing, esp. from multiple providers. There is nothing to indicate who entered or when it was entered. | Done | 1 | kyle.cardwell@va.gov | MHV Sprint 144 VA.gov MR | C109083
MHV-64622 | Pre release-Priority 4: Some allergies do not display all applicable allergy types | Done | 1 | kyle.cardwell@va.gov | MHV Sprint 144 VA.gov MR | C109084
MHV-64969 | Verify vaccine occurrence date/time is correct (thread in Slack) | Done |  | john.moehrke@va.gov | MHV Sprint 145 VA.gov MR | QA Comment: No QA subtask
MHV-64355 | Dec 4 - Deploy MHV-54036, MHV-61973, MHV-63830 along with FE changes (tickets HERE) | Done |  | muazzam.khan@va.gov | MHV Sprint 145 VA.gov MR | QA Comment: back end test /no test case required
MHV-64539 | Launch Blocker/Audit: Update PDF and TXT for Pathology | Done | 1 | matthew.wright8@va.gov | MHV Sprint 145 VA.gov MR | C109085
MHV-64540 | Launch Blocker/Audit: Update PDF and TXT for CHEM/HEM | Done | 1 | matthew.wright8@va.gov | MHV Sprint 145 VA.gov MR | C109086
MHV-64541 | Launch Blocker/Audit: Update PDF and TXT for Microbiology | Done | 1 | matthew.wright8@va.gov | MHV Sprint 145 VA.gov MR | C109087
MHV-64548 | Launch Blocker/Audit: Update PDF and TXT for Allergies | Done | 1 | matthew.wright8@va.gov | MHV Sprint 145 VA.gov MR | C109088
MHV-64620 | Pre release-Priority 1: Entire browser crashes on iOS safari when attempting to download any feature .pdf. This does not occur when looking at the PDF generated for print. | Done | 1 | michael.moyer@va.gov | MHV Sprint 145 VA.gov MR | QA Comment: no test case required
MHV-64617 | Pre Release-Priority 7: .txt file download of single vaccine labels the date administered as "Date entered" | Done | 1 | justin.lattimore@va.gov | MHV Sprint 145 VA.gov MR | C109089
MHV-64623 | MyGoals content update | Done | 1 | kyle.cardwell@va.gov | MHV Sprint 145 VA.gov MR | Will not make Phase 1 release.
MHV-64927 | Imaging breadcrumb updates | Done | 3 | victoria.saleem@va.gov | MHV Sprint 145 VA.gov MR | Maruf
MHV-61461 | Sept staging review-Update the title tags for all the details pages in the Medical Record | Done | 2 | oleksii.morgun@va.gov | MHV Sprint 145 VA.gov MR | C109090
MHV-65020 | Move txt generation into new download UI | Done | 1 | kolby.balch@va.gov | MHV Sprint 145 VA.gov MR | QA Comment: no test case required
MHV-64791 | Launch Blocker: Focus Issue on share your electronic health record | Done | 2 | kyle.cardwell@va.gov | MHV Sprint 145 VA.gov MR | Check with Bryan/Mike
MHV-65052 | Resolve breadcrumb issues for Phase 1 | Done | 2 | victoria.saleem@va.gov | MHV Sprint 145 VA.gov MR | QA Comment: no test case required
MHV-65032 | UI Fixes on Download Records | Done | 2 | kolby.balch@va.gov | MHV Sprint 145 VA.gov MR | C109079
MHV-65081 | Error on first load of images, upon refresh it works | Done | 1 | michael.moyer@va.gov | MHV Sprint 145 VA.gov MR | QA Comment: No QA subtask
MHV-65059 | Handle API errors in BB Medical Downloads | Done | 2 | michael.moyer@va.gov | MHV Sprint 145 VA.gov MR | QA Comment: no test case required
MHV-64984 | Focus issue when using tab key only on list view links-All domains | Done | 3 | kyle.cardwell@va.gov | MHV Sprint 145 VA.gov MR | QA Comment: no test case required
MHV-62493 | Add Datadog Monitoring for Download of Self Entered Health History | Done | 2 | Tywande.Barnes@va.gov | MHV Sprint 145 VA.gov MR | QA Comment: no test case required
MHV-60682 | Update status checks to use multiple extract types for Labs & Tests | Done | 2 | michael.moyer@va.gov | MHV Sprint 145 VA.gov MR | Check with Bryan/Mike
MHV-62597 | Create MR playbook for acknowledging and responding to alerts and monitoring - GH# 95646 | To Do | 2 | michael.moyer@va.gov | MHV Sprint 145 VA.gov MR | QA Comment: No QA subtask
MHV-65164 | Ensure that BB action handles both labs & tests and radiology calls | Done | 1 | michael.moyer@va.gov | MHV Sprint 145 VA.gov MR | QA Comment: back end test /no test case required
MHV-64881 | Enumerate and handle newlines for all comment fields | Done | 1 | kyle.cardwell@va.gov | MHV Sprint 145 VA.gov MR | QA Comment: No QA subtask
MHV-64889 | Update OH messaging for MR Users | Done | 2 | kyle.cardwell@va.gov | MHV Sprint 145 VA.gov MR | Maruf
MHV-62579 | Appointment Data not appearing on PDF | Done | 2 | matthew.wright8@va.gov | MHV Sprint 145 VA.gov MR | Check with Bryan/Mike
MHV-65298 | Settings Updates found in Testing | Done | 1 | Tywande.Barnes@va.gov | MHV Sprint 145 VA.gov MR | QA Comment: No QA subtask
MHV-65053 | IA Audit fixes (non breadcrumb) | Done | 2 | matthew.wright8@va.gov | MHV Sprint 145 VA.gov MR | C10990
MHV-63077 | PDF Cover page creation | Done | 3 | adrian.rollett@va.gov | MHV Sprint 145 VA.gov MR | C10991
MHV-65069 | Self Entered PDF - Add error handling and resolve API issues | Done | 3 | matthew.wright8@va.gov | MHV Sprint 145 VA.gov MR | Merged, subtask needs testing-- Maruf
MHV-65160 | Resolve appointments/Military service call issues | Done | 2 | michael.moyer@va.gov | MHV Sprint 145 VA.gov MR | Merged, subtask needs testing-- Maruf
MHV-64949 | Update content on settings page | Done | 2 | matthew.wright8@va.gov | MHV Sprint 145 VA.gov MR | Merged, subtask needs testing-- Maruf
MHV-65070 | Resolve TXT download errors | Done | 3 | michael.moyer@va.gov | MHV Sprint 145 VA.gov MR | Merged, subtask needs testing-- Maruf
MHV-65315 | For BB download, appointment query dates are wrong | Done | 1 | matthew.wright8@va.gov | MHV Sprint 145 VA.gov MR | QA Comment: No QA subtask
MHV-65297 | Self Entered Updates found in Testing | Done | 2 | kyle.cardwell@va.gov | MHV Sprint 145 VA.gov MR | QA Comment: No QA subtask
MHV-65293 | Self-entered pdf download spinner | Done | 1 | matthew.wright8@va.gov | MHV Sprint 145 VA.gov MR | QA Comment: no test case required
MHV-64668 | Stress test performance of a PDF generation Download all | Done | 2 | sanjay.gupta1@va.gov | MHV Sprint 145 VA.gov MR | Tested with 10,000 record PDF no isuues -- C109092
MHV-62491 | Add Datadog Monitoring for Download All | Ready for Validation | 1 | Tywande.Barnes@va.gov | MHV Sprint 145 VA.gov MR | Validated, Mike to add monitor and then close
MHV-65229 | Resolve remaining UI/Acc issues - Download All | Ready for Validation | 2 | kyle.cardwell@va.gov | MHV Sprint 145 VA.gov MR | Holding to merge until after staging review
MHV-65295 | TXT File Updates found in Testing | In Progress | 2 | kyle.cardwell@va.gov | MHV Sprint 145 VA.gov MR
MHV-65064 | Resolve download accessibility findings (GH 98932) | In Progress | 2 | victoria.saleem@va.gov | MHV Sprint 145 VA.gov MR
MHV-65022 | Resolve imaging accessibility findings (GH 98846) | In Progress | 2 | kolby.balch@va.gov | MHV Sprint 145 VA.gov MR
MHV-65317 | BB PDF Download with medications selected does not have Allergies | In Progress | 2 | michael.moyer@va.gov | MHV Sprint 145 VA.gov MR
MHV-65314 | If CCD has an error, the alert only appears after reloading | To Do | 2 | kolby.balch@va.gov | MHV Sprint 145 VA.gov MR
MHV-65296 | Download BB Updates found in Testing | To Do | 2 | michael.moyer@va.gov | MHV Sprint 145 VA.gov MR
MHV-65299 | Lab/Test Updates found in Testing | To Do | 2 | michael.moyer@va.gov | MHV Sprint 145 VA.gov MR
MHV-65300 | TXT/PDF Updates found in Testing | To Do | 2 | michael.moyer@va.gov | MHV Sprint 145 VA.gov MR
MHV BACKEND
MHV-64996 | Interim - Notify if image download fails | In Progress | 3 | muazzam.khan@va.gov | MHV Sprint 145 VA.gov MR | 12/18 deploy targeted
MHV-60776 | Implement - Collapse and condense the "Try Me" information boxes to a universal Try Me box for Secure Messaging, Medications and Medical Records. | Ready for Validation | 2 | brittany.clausen@va.gov | Access/Portals Sprint 145 | Planned - update Brittany with date to push
Discussions to have, Launch Blocker?
MHV-65237 | Misc Issues to Triage
LINK TO FAST FOLLOW ITEMS HERE

## Fast Follow
Issue key | Summary | Pts | Assignee | Description | Section | Labels | BR Notes
MHV-65323 | Download xml Error not being announced by Screen Reader | 2 |  | Please reference subtask [https://jira.devops.va.gov/browse/MHV-65040] for findings from previous ticket. On the Download your VA Blue Button report page, if an error is generated while attempting to download .xml file, it is not announced by the screen reader. | Download BB | Accessibility | MHV-65229 (Ready for Validation) fixes many Download Acc issues (perhaps not this) - retest after it merges.
MHV-65316 | Resolve browser back focus issue |  |  | whenever the user uses the browser back/forward buttons, the backToTop component isn't automatically scrolling them to the top | Throughout App | Accessibility/Focus | Still an issue
MHV-65313 | UI/Acc issue - Select records and download report child form pages | 2 | alexia.wunder@va.gov | The Select records and download report has 3 different child form pages - Select date range, Select types of records to include, and Select file type. When user relying on a screen reader navigates through the child form pages they hear "Select records and download report" on all three of them. This is confusing to the user as they wouldn't know that they are on a different child form page. | Download BB | Accessibility | MHV-65229 (Ready for Validation) fixes many Download Acc issues - retest after it merges.
MHV-65294 | UCD Fast Follow Clarifications |  | alexia.wunder@va.gov | Items we need clarification/help from UCD (fast follow): Â *UCD HELP* # If you try to share and it fails, you have to navigate away and come back before the button reappears - {color:#ff0000}*LATER?Â Need UCD*{color} # {color:#172b4d}Need clarification on the 'Any' date range.Â Currently a user selects 'Any' - we feel it maybe should be 'All'.Â In addition to the dropdown, we'd want clarification on the subsequent screens as well for a good flow.Â Â {color} # Had to introduce date range of Any to Any in order to ensure download would still work.Â Will need UX help/cleanup - {color:#ff0000}*LATER?Â Need UCD*{color} # {color:#172b4d}There are discrepancies between PDF and TXT - likely driven by the PDF redesign.Â Below is one example of several where the discrepancies need to be reviewed and cleaned up {color}- {color:#ff0000}*LATER?Â Need UCD and need to verify similarities between UI, PDF, and TXT.*{color} Txt file is showing this but PDF is not showing the following: What to know about your Blue Button report - If you print or download your Blue Button report, you'll need to take responsibility for protecting the information in the report. - Some records in this report are available 36 hours after providers enter them. This includes care summaries and notes, health condition records, and most lab and test results. - This report doesn't include information you entered yourself. To find information you entered yourself, go back to the previous version of Blue Button on the My HealtheVet website. => This text (the last line) may not be updated...PDF shows it as ' Note: This report doesn't include information you entered yourself. To find information you entered yourself, download a self-entered health information report. Need help? - If you have questions about this report or you need to add information to your records, send a secure message to your care team. - If you're ever in crisis and need to talk with someone right away, call the Veterans Crisis Line at 988. Then select 1. Text file has this warning, PDF doesn't have: 'If your results are outside the reference range, this doesn't automatically mean you have a health problem. Your provider will explain what your' | UCD Clarification | UCD Clarification | For UCD to clarify requirements
MHV-65243 | Remove 'Stay on this page until your records load' from PHR refresh load state | [5 empty] | Unknown - need more detail
MHV-65159 | Update text of 'Count of total records' to be more intuitive on download | 2 |  | Need detail updated |  |  | Unknown - need more detail
MHV-65044 | Notify user of image download failure using VA Notify (future) | 3 |  | Notify user of image download failure using VA Notify (future) User Story:*Â As a MR user, I want to be notified if my request for radiology images fails, so that I am aware of the problem. Â *GIVEN:* User requests images *WHEN:* The system has a failure pulling the radiology images *THEN:* The user receives an email generated by VA Notify to inform them of the failure Â *Feature Flag Y/N ?* *DataDog AnalyticsÂ Y/N ?* *Manual Testing Y/N ?*Â *Automated Testing Y/N ?*Â *Accessibility Testing Y/N ?*Â *UCD Validation Y/N* Â *Acceptance Criteria:* AC1Â Â AC2Â Â AC3 AC4 Â *Links to UCD:* Figma Link: Other Design Notes: | Imaging | VA Notify | Queue for future integration, handled in interim by existing MHV messaging
MHV-64970 | Research: Radiology, Vitals, Download all etc Timezone |  | michael.moyer@va.gov | We saw a case where a Dec 27, 2013 at 21:15 radiology study rolled over to Dec 28, 2013 at 2:15 AM in the new MR. User is in Texas (Central), appt was in Phoenix (Mountain) Â * Timezone isn't displaying correctly * !image-2024-12-10-22-08-56-073.png¦width=390,height=157! Â Â Â This was reported on Vitals too (missing): Â !image-2024-12-10-22-14-55-924.png¦width=764,height=194! | Throughout App | Time/Time Zones | Need to meet about timezones, in some areas we cannot adjust or modify by design. In other areas we may have some flexibility.
MHV-64968 | Verify field name and source for lab/location - check w Kaitlin/Lexi |  | michael.moyer@va.gov | Verify field name and source for lab/location - check w Kaitlin/Lexi Â Â *Feature Flag Y/N ?* *DataDog AnalyticsÂ Y/N ?* *Manual Testing Y/N ?*Â *Automated Testing Y/N ?* *Accessibility Testing Y/N ?* *UCD Validation Y/N* Â *Acceptance Criteria:* AC1 AC2 AC3 AC4 Â *Links to UCD:* Figma Link: Other Design Notes: Â Â | UCD Clarification | UCD Clarification | For UCD to clarify requirements
MHV-64615 | Pre release-Priority 2: History of Lab Comment edits is visible to user, vs. simply displaying the last value entered | 1 | michael.moyer@va.gov | Pre release-Priority 2: History of Lab Comment edits is visible to user, vs. simply displaying the last value entered in a given analyte and noting that the test record was amended # Log into MR on Staging as test user Gustav 2. Go to Labs and Tests 3. View the test conducted on 12 Nov 2024 (Gen Chem Specimen) 4. Observe data in Lab Comments field 5. Compare to MHV Classic list and detail view for .RBC analyte (test is listed as Bone marrow structure (body structure){*}{{*}}Â **Â Amended notes are simply denoted as "amended" in MHV Classic. Â In the new experience, every change is being displayed in detail. Â *Domain:*Â Labs [MR Phase 1 Bugs.xlsx (sharepoint.com)¦https://dvagov.sharepoint.com/:x:/s/MedicalRecordsonVA.govTestData/Ee51aiLKu3JLs8ubVUiske8BS-j555fa6mKhN7KvfIL_SQ?e=sRLzUV] Â *GIVEN:* *WHEN:* *THEN:* Â *Feature Flag Y/N ?* *DataDog AnalyticsÂ Y/N ?* *Manual Testing Y/N ?* Y-Sanjay *Automated Testing Y/N ?* *Accessibility Testing Y/N ?* *UCD Validation Y/N* Â *Acceptance Criteria:* AC1Â Â Simply display the last value entered in a given analyte and noting that the test record was amended instead of whole history AC2 AC3 AC4 Â *Links to UCD:* Figma Link: Other Design Notes: Â Â | Throughout App | Data | To be prioritized
MHV-64614 | Post release: Field for Provider notes is displayed on MHV on VA.gov when no such field exists in CPRS. | 1 |  | Post release: Â Field for Provider notes is displayed on MHV on VA.gov when no such field exists in CPRS. Â As a result, MHV always shows "none noted" in the field. Triple check this is true in VistA MHVC Blue Button shows a "Comments" field for Vitals which appears to always return "--" *Domain:* Vitals [MR Phase 1 Bugs.xlsx (sharepoint.com)¦https://dvagov.sharepoint.com/:x:/s/MedicalRecordsonVA.govTestData/Ee51aiLKu3JLs8ubVUiske8BS-j555fa6mKhN7KvfIL_SQ?e=sRLzUV] *GIVEN:* *WHEN:* *THEN:* Â *Feature Flag Y/N ?* *DataDog AnalyticsÂ Y/N ?* *Manual Testing Y/N ?*Â *Automated Testing Y/N ?* *Accessibility Testing Y/N ?* *UCD Validation Y/N* Â *Acceptance Criteria:* AC1Â Â AC2 AC3 AC4 Â *Links to UCD:* Figma Link: Other Design Notes: Â Â | Throughout App | Data | To be prioritized
MHV-64613 | Post release: Location where historical vaccine was given shows the name of the VistA instance and not the outside location entered in CPRS | 1 |  | Post release: Â Location where historical vaccine was given shows the name of the VistA instance and not the outside location entered in CPRS 1. Log into Staging as test patient Silva 2. Select Vaccines 3. Select Influenza, Recombinant Trivalent, PF entry with a Date Received of Oct 20, 2023 4. Observe that the location shows CHYSHR TEST LAB 5. Sign into CPRS CHYSHR instance 6. Select patient Silva 7. Go to the Note tab at the bottom of the page 8. Select the fourth Oct 18, 2024 Outpatient Note, from a visit at GREELEY NURSE. Â 9. Observe that the note detail shows that the visit occurred at COVID VACCINE CLIN1 Â *Domain:* Vaccines [MR Phase 1 Bugs.xlsx (sharepoint.com)¦https://dvagov.sharepoint.com/:x:/s/MedicalRecordsonVA.govTestData/Ee51aiLKu3JLs8ubVUiske8BS-j555fa6mKhN7KvfIL_SQ?e=sRLzUV] Â *GIVEN:* *WHEN:* *THEN:* Â *Feature Flag Y/N ?* *DataDog AnalyticsÂ Y/N ?* *Manual Testing Y/N ?*Â *Automated Testing Y/N ?* *Accessibility Testing Y/N ?* *UCD Validation Y/N* Â *Acceptance Criteria:* AC1Â Â AC2 AC3 AC4 Â *Links to UCD:* Figma Link: Other Design Notes: [MR Phase 1 Bugs.xlsx (sharepoint.com)¦https://dvagov.sharepoint.com/:x:/s/MedicalRecordsonVA.govTestData/Ee51aiLKu3JLs8ubVUiske8BS-j555fa6mKhN7KvfIL_SQ?e=sRLzUV] Â | Throughout App | Data | To be prioritized
MHV-64612 | Post release: "Where can I findâ€¦" FAQ drawer text does not match MR designs | 1 |  | Post release: Â "Where can I findâ€¦" FAQ drawer text does not match MR designs Â *Domain:* Landing [MR Phase 1 Bugs.xlsx (sharepoint.com)¦https://dvagov.sharepoint.com/:x:/s/MedicalRecordsonVA.govTestData/Ee51aiLKu3JLs8ubVUiske8BS-j555fa6mKhN7KvfIL_SQ?e=sRLzUV] Â *GIVEN:* *WHEN:* *THEN:* Â *Feature Flag Y/N ?* *DataDog AnalyticsÂ Y/N ?* *Manual Testing Y/N ?*Â *Automated Testing Y/N ?* *Accessibility Testing Y/N ?* *UCD Validation Y/N* Â *Acceptance Criteria:* AC1Â Â AC2 AC3 AC4 Â *Links to UCD:* Figma Link: Other Design Notes: Â Â | Content | FAQ | To be prioritized
MHV-64611 | Post release: Location health conditions were recorded displayed inaccurately | 1 |  | Post release: Â Â Location health conditions were recorded displayed inaccurately # Log into MR on Staging at test user Silva 2. Go to Health Conditions 3. Select Allergic Rhinitis 4. Observe Location field Matches incorrect behavior in MHVC; will revisit after Phase 1 launch *Domain:* Health Conditions [MR Phase 1 Bugs.xlsx (sharepoint.com)¦https://dvagov.sharepoint.com/:x:/s/MedicalRecordsonVA.govTestData/Ee51aiLKu3JLs8ubVUiske8BS-j555fa6mKhN7KvfIL_SQ?e=sRLzUV] Â *GIVEN:* *WHEN:* *THEN:* Â *Feature Flag Y/N ?* *DataDog AnalyticsÂ Y/N ?* *Manual Testing Y/N ?*Â *Automated Testing Y/N ?* *Accessibility Testing Y/N ?* *UCD Validation Y/N* Â *Acceptance Criteria:* AC1Â Â AC2 AC3 AC4 Â *Links to UCD:* Figma Link: Other Design Notes: Â Â | Throughout App | Data | To be prioritized
MHV-64610 | Post release: Incorrect location shown for location note was entered | 1 |  | Post release: Â Â Incorrect location shown for location note was entered # Log into MR on Staging at test user Silva # Go to Care Notes and Summaries Matches behavior in MHVC; will revisit after Phase 1 launch *Domain:* Care Notes [MR Phase 1 Bugs.xlsx (sharepoint.com)¦https://dvagov.sharepoint.com/:x:/s/MedicalRecordsonVA.govTestData/Ee51aiLKu3JLs8ubVUiske8BS-j555fa6mKhN7KvfIL_SQ?e=sRLzUV] *GIVEN:* *WHEN:* *THEN:* Â *Feature Flag Y/N ?* *DataDog AnalyticsÂ Y/N ?* *Manual Testing Y/N ?*Â *Automated Testing Y/N ?* *Accessibility Testing Y/N ?* *UCD Validation Y/N* Â *Acceptance Criteria:* AC1Â Â AC2 AC3 AC4 Â *Links to UCD:* Figma Link: Other Design Notes: Â Â | Throughout App | Data | To be prioritized
MHV-64609 | Post release: Notes with multiple identified cosigners are released to users after one signature | 1 |  | Post release: Â Â Notes with multiple identified cosigners are released to users after one signature # Log into MR on Staging at test user Silva 2. Go to Care Notes and Summaries Matches behavior in MHVC; will revisit after Phase 1 launch *Domain:* Care Notes [MR Phase 1 Bugs.xlsx (sharepoint.com)¦https://dvagov.sharepoint.com/:x:/s/MedicalRecordsonVA.govTestData/Ee51aiLKu3JLs8ubVUiske8BS-j555fa6mKhN7KvfIL_SQ?e=sRLzUV] Â *GIVEN:* *WHEN:* *THEN:* Â *Feature Flag Y/N ?* *DataDog AnalyticsÂ Y/N ?* *Manual Testing Y/N ?*Â *Automated Testing Y/N ?* *Accessibility Testing Y/N ?* *UCD Validation Y/N* Â *Acceptance Criteria:* AC1Â Â AC2 AC3 AC4 Â *Links to UCD:* Figma Link: Other Design Notes: Â Â | Throughout App | Data | To be prioritized
MHV-64608 | Post release: List view txt file is missing text shown on the PDF Figma Mockup. | 1 |  | Post release: Â Â List view txt file is missing text shown on the PDF Figma Mockup. Inconsistent language from what is shown in the PDF mockup (did not see a mockup for TXT) Â *Domain:* Allergies [MR Phase 1 Bugs.xlsx (sharepoint.com)¦https://dvagov.sharepoint.com/:x:/s/MedicalRecordsonVA.govTestData/Ee51aiLKu3JLs8ubVUiske8BS-j555fa6mKhN7KvfIL_SQ?e=sRLzUV] Â *GIVEN:* *WHEN:* *THEN:* Â *Feature Flag Y/N ?* *DataDog AnalyticsÂ Y/N ?* *Manual Testing Y/N ?*Â *Automated Testing Y/N ?* *Accessibility Testing Y/N ?* *UCD Validation Y/N* Â *Acceptance Criteria:* AC1Â Â AC2 AC3 AC4 Â *Links to UCD:* Figma Link: Other Design Notes: Â Â | Download BB | TXT File | Need detail updated
MHV-64607 | Post release: PDFs generated for print and for download are missing text shown in Figma mockup | 1 |  | Post release: Â Â PDFs generated for print and for download are missing text shown in Figma mockup Most of the text shown right below the "If you're ever in crisis" note is not shown in either version of the PDF *Domain:* Allergies [MR Phase 1 Bugs.xlsx (sharepoint.com)¦https://dvagov.sharepoint.com/:x:/s/MedicalRecordsonVA.govTestData/Ee51aiLKu3JLs8ubVUiske8BS-j555fa6mKhN7KvfIL_SQ?e=sRLzUV] *GIVEN:* *WHEN:* *THEN:* Â *Feature Flag Y/N ?* *DataDog AnalyticsÂ Y/N ?* *Manual Testing Y/N ?*Â *Automated Testing Y/N ?* *Accessibility Testing Y/N ?* *UCD Validation Y/N* Â *Acceptance Criteria:* AC1Â Â AC2 AC3 AC4 Â *Links to UCD:* Figma Link: Other Design Notes: Â Â | Download BB | PDF File | Need detail updated
MHV-64606 | Post release: .pdf download of full allergy list formats reactions in a way that is difficult to read | 1 |  | Post release: Â .pdf download of full allergy list formats reactions in a way that is difficult to read Each reaction is listed in all caps and separated by a period and a space. Figma file shows an allergy with a single reaction, so there is no mockup to compare with. *Domain:* Allergies [MR Phase 1 Bugs.xlsx (sharepoint.com)¦https://dvagov.sharepoint.com/:x:/s/MedicalRecordsonVA.govTestData/Ee51aiLKu3JLs8ubVUiske8BS-j555fa6mKhN7KvfIL_SQ?e=sRLzUV] Â *GIVEN:* *WHEN:* *THEN:* Â *Feature Flag Y/N ?* *DataDog AnalyticsÂ Y/N ?* *Manual Testing Y/N ?*Â *Automated Testing Y/N ?* *Accessibility Testing Y/N ?* *UCD Validation Y/N* Â *Acceptance Criteria:* AC1 Â .pdf download of full allergy list formats reactions in a way that is easy to read AC2 AC3 AC4 Â *Links to UCD:* Figma Link: Other Design Notes: Â Â | Download BB | PDF File | To be prioritized
MHV-64605 | Post release: "Last Updated" at top of page omits user's time zone | 1 |  | Post release: Â "Last Updated" at top of page omits user's time zone "Last Updated" at top of page omits user's time zone, which is included in all MR designs. *All Domains* [MR Phase 1 Bugs.xlsx (sharepoint.com)¦https://dvagov.sharepoint.com/:x:/s/MedicalRecordsonVA.govTestData/Ee51aiLKu3JLs8ubVUiske8BS-j555fa6mKhN7KvfIL_SQ?e=sRLzUV] Â *GIVEN:* *WHEN:* *THEN:* Â *Feature Flag Y/N ?* *DataDog AnalyticsÂ Y/N ?* *Manual Testing Y/N ?*Â *Automated Testing Y/N ?* *Accessibility Testing Y/N ?* *UCD Validation Y/N* Â *Acceptance Criteria:* AC1 Â "Last Updated" at top of page no longer omits user's time zone AC2 AC3 AC4 Â *Links to UCD:* Figma Link: Other Design Notes: Â Â | Throughout App | Time/Time Zones | Need to meet about timezones, in some areas we cannot adjust or modify by design. In other areas we may have some flexibility.
MHV-64588 | Discovery/Research Idea: Health Conditions: No time delay exists between Health Condition entry in CPRS and appearance on MHV |  |  | *This ticket is an idea coming out of pre-Phase 1.Â We need to the business to determine if they'd like to move forward with it.* Â No time delay exists between Health Condition entry in CPRS and appearance on MHV Steps to Reproduce: 1. Sign into CPRS CHYSHR instance 2. Select patient Silva 3. Go to Problems tab at bottom of screen 4. Click New problem button in left column near top 5. Enter a new health condition 6. Note the date and time 7. Log into Staging as patient Silva at least an hour after, but before 36 hours have elapsed from time condition was entered in CPRS 8. Select Health Conditions 9. Observe the most recently recorded condition Â Comments: -Not sure whether this is a requirement, but MHV text states it is expected -Matches behavior in MHVC. Will review this with OCC post-launch to confirm this is the desired behavior | Enhancement Idea |  | Need stakeholder input and requirements and then prioritize
MHV-64587 | Discovery/Research Idea: Care Summ/Notes: No time delay exists between note signature in CPRS and appearance on MHV |  |  | *This ticket is an idea coming out of pre-Phase 1.Â We need to the business to determine if they'd like to move forward with it.* Â No time delay exists between note signature in CPRS and appearance on MHV Steps to Reproduce: 1. Sign into CPRS CHYSHR instance 2. Select patient Silva 3. Enter a new Vaccine record, which will generate an Outpatient note. 4. Log into Staging as patient Silva at least an hour after, but before 36 hours have elapsed from time note was entered in CPRS 8. Select Notes 9. Observe the most recently recorded Outpatient note is visible less than 36 hours noted on the page Â Note this is a different entry from the *Soy* allergy entered on 9/23/2024 Â Comments: -Believe this delay is a requirement? -The Outpatient note observed within the delay window was for a vaccine entered early the same day, but the vaccine record itself was not shown on the vaccines page. This is consistent with the behavior of MHV Classic. Â Current behavior is mitigated by disclaimer at the top of the page stating "{*}Most{*} care summaries and notes are available 36 hours after providers sign them" Â Will revisit after launch to determine what desired behavior should be. Â It is unclear to me the difference between the Signs/Symptoms date and the Reaction Date/Time in CPRS. Each symptom defaults to NOW, but can have a distinct date while Reaction is a single entry. | Enhancement Idea |  | Need stakeholder input and requirements and then prioritize
MHV-64586 | Discovery/Research Idea: Allergies: Historical allergies display only the date entered into EHR even when other dates are available |  |  | *This ticket is an idea coming out of pre-Phase 1.Â We need to the business to determine if they'd like to move forward with it.* Â Historical allergies display only the date entered into EHR even when other dates are available Steps to Reproduce: 1. Sign into MR Staging as test patient Silva 2. Go to Allergies 4. Select *Soy Products* allergy dated 11/20/2024 5. Compare to CPRS SLC10, where distinct dates were entered (11/20/2024), reaction date 5/1/2024, and Signs/Symptons date is 10/9/2024. Â Note this is a different entry from the *Soy* allergy entered on 9/23/2024 Â Comments: -We believe using the latter would be more medically informative for users and non-VA caregivers -I also noted in the comments the various dates used during data entry. Â Reaction date or sign/symptoms date is more relevant to the allergy than the date it was entered into CPRS. Â It is unclear to me the difference between the Signs/Symptoms date and the Reaction Date/Time in CPRS. Each symptom defaults to NOW, but can have a distinct date while Reaction is a single entry. | Enhancement Idea |  | Need stakeholder input and requirements and then prioritize
MHV-64585 | Discovery/Research Idea: Allergies: Observed allergies displayed only the date entered into EHR even when other dates for Observed and Signs/Symptoms were entered in CPRS |  |  | *This ticket is an idea coming out of pre-Phase 1.Â We need to the business to determine if they'd like to move forward with it.* Â *Observed* allergies displayed only the date entered into EHR even when other dates for Observed and Signs/Symptoms were entered in CPRS Steps to Reproduce: 1. Sign into MR Staging as test patient Gustav 2. Go to Allergies 4. Select Coconuts allergy dated 11/20/2024 5. Compare to CPRS SLC10 where sign/sympton Pruritis is dated 11/8/2024, sign/symptom delrium is dated 11/8/2024, origination date is 11/20/2024, and reaction date is 11/14/2024. Â Comments: -We believe using the latter would be more medically informative for users and non-VA caregivers -I also noted in the comments the various dates used during data entry. Reaction date or sign/symptoms date is more relevant to the allergy than the date it was entered into CPRS. It is unclear to me the difference between the Signs/Symptoms date and the Reaction date in CPRS. Each symptom defaults to NOW, but can have a distinct date while Reaction is a single entry. | Enhancement Idea |  | Need stakeholder input and requirements and then prioritize
MHV-64556 | Audit: Update PDF and TXT for Vitals | 1 |  | Audit: Update PDF and TXT for Vitals Note:Â This was also mentioned in the Phase 1 bug spreadsheet, line item 30 ¦.txt of selected vital inserts random "details about this test" text¦ 1-Remove domain prefix (ticket for this already exists). 2-"VA Medical Record" should be removed. 3-Font style should be PDF body font. 4-Need to add "Showing # records from newest to oldest. (TXT) 5-Remove "Date entered:" and "Details about this test" text to align with PDF. (TXT) 6- Remove "Date entered:" and "Details about this test" text to align with PDF. (Not is screen shotâ€“see mural board) !Vitals PDF TXT.PNG¦thumbnail! Â Â *[MR - UCD Audits â€¢ Department of Veterans Affairs (mural.co)¦https://app.mural.co/t/departmentofveteransaffairs9999/m/departmentofveteransaffairs9999/1685987646356/dde9adf5fd24b6e5d2431a77cb13ea15bf4b6cab]* *GIVEN:* *WHEN:* *THEN:* Â *Feature Flag Y/N ?* *DataDog AnalyticsÂ Y/N ?* *Manual Testing Y/N ?* Y-Maruf *Automated Testing Y/N ?* *Accessibility Testing Y/N ?* *UCD Validation Y/N* Â *Acceptance Criteria:* AC1 Â PDF has been updated with corrections noted AC2 AC3 AC4 Â *Links to UCD:* Figma Link: Other Design Notes: Â Â | Download BB | TXT File, PDF File | To be prioritized
MHV-64554 | Audit: Update Vitals list page | 1 |  | Audit: Update Vitals list page 1-Time should be removed. !Vitals List page.PNG¦thumbnail! Â Â *[MR - UCD Audits â€¢ Department of Veterans Affairs (mural.co)¦https://app.mural.co/t/departmentofveteransaffairs9999/m/departmentofveteransaffairs9999/1685987646356/dde9adf5fd24b6e5d2431a77cb13ea15bf4b6cab]* *GIVEN:* *WHEN:* *THEN:* Â *Feature Flag Y/N ?* *DataDog AnalyticsÂ Y/N ?* *Manual Testing Y/N ?* Y-Maruf *Automated Testing Y/N ?* *Accessibility Testing Y/N ?* *UCD Validation Y/N* Â *Acceptance Criteria:* AC1Â Vitals list page has been updated with corrections noted AC2 AC3 AC4 Â *Links to UCD:* Figma Link: Other Design Notes: Â Â | List Page | Time/Time Zones | Need to meet about timezones, in some areas we cannot adjust or modify by design. In other areas we may have some flexibility.
MHV-64553 | Audit: Update PDF and TXT for Health Conditions | 1 |  | Audit: Update PDF and TXT for Allergies {*}Note{*}:Â This is listed in the Phase 1 bug spreadsheet, line item 19. ¦"About the code in this condition name" text is missing from .pdf and .txt downloads¦ 1- Remove domain prefix (ticket for this already exists). 2- Missing "About the code ..." field and text. Figma link: [https://www.figma.com/design/SGP1z2LejUWqDZyT61po5J/Medical-Records---Phase-1?node-id=5565-73924&t=VEjIGenRR3nuSMmV-1]Â 3- "Date entered:" text should appear above "Provider:" in data group (TXT) !Health Conditions PDF and txt.PNG¦thumbnail! Â Â *[MR - UCD Audits â€¢ Department of Veterans Affairs (mural.co)¦https://app.mural.co/t/departmentofveteransaffairs9999/m/departmentofveteransaffairs9999/1685987646356/dde9adf5fd24b6e5d2431a77cb13ea15bf4b6cab]* *GIVEN:* *WHEN:* *THEN:* Â *Feature Flag Y/N ?* *DataDog AnalyticsÂ Y/N ?* *Manual Testing Y/N ?* Y-Maruf *Automated Testing Y/N ?* *Accessibility Testing Y/N ?* *UCD Validation Y/N* Â *Acceptance Criteria:* AC1 Â PDF has been updated with corrections noted AC2 AC3 AC4 Â *Links to UCD:* Figma Link: Other Design Notes: Â Â | Download BB | TXT File, PDF File | To be prioritized
MHV-64552 | Audit: Update Health Conditions Details page | 1 |  | Audit: Update Health Conditions Details page 1- Remove domain prefix (ticket for this already exists). 2-Too much space between field and data. Text line height should be 1.5 Â Note:Â There is also a yellow stickie that says: Â When using browser's back functionality, the user is brought to the bottom of the previous screen. Please check Health Conditions details page to see if this applies. !Health condtions details.PNG¦thumbnail! *[MR - UCD Audits â€¢ Department of Veterans Affairs (mural.co)¦https://app.mural.co/t/departmentofveteransaffairs9999/m/departmentofveteransaffairs9999/1685987646356/dde9adf5fd24b6e5d2431a77cb13ea15bf4b6cab]* *GIVEN:* *WHEN:* *THEN:* Â *Feature Flag Y/N ?* *DataDog AnalyticsÂ Y/N ?* *Manual Testing Y/N ?* Y-Sanjay *Automated Testing Y/N ?* *Accessibility Testing Y/N ?* *UCD Validation Y/N* Â *Acceptance Criteria:* AC1Â HC details page has been updated with corrections noted AC2 AC3 AC4 Â *Links to UCD:* Figma Link: Other Design Notes: Â Â | Details page |  | To be prioritized
MHV-64551 | Audit: Update PDF and TXT for Allergies | 1 |  | Audit: Update PDF and TXT for Allergies 1- Remove domain prefix (ticket for this already exists). 2-Remove extra space between lines. 3-"Date entered:" should be moved to be above "Signs and symptoms:" field. (TXT) 4- "A" should be lowercase. (TXT) !Allergies PDF and TXT files.PNG¦thumbnail! Â *[MR - UCD Audits â€¢ Department of Veterans Affairs (mural.co)¦https://app.mural.co/t/departmentofveteransaffairs9999/m/departmentofveteransaffairs9999/1685987646356/dde9adf5fd24b6e5d2431a77cb13ea15bf4b6cab]* *GIVEN:* *WHEN:* *THEN:* Â *Feature Flag Y/N ?* *DataDog AnalyticsÂ Y/N ?* *Manual Testing Y/N ?* Y-Maruf *Automated Testing Y/N ?* *Accessibility Testing Y/N ?* *UCD Validation Y/N* Â *Acceptance Criteria:* AC1 Â PDF and TXT has been updated with corrections noted AC2 AC3 AC4 Â *Links to UCD:* Figma Link: Other Design Notes: Â Â | Download BB | TXT File, PDF File | To be prioritized
MHV-64549 | Audit: Update Allergies Details page | 1 |  | Audit: Update Allergies Details page 1- Remove domain prefix (ticket for this already exists). 2-Too much space between field and data. Text should have line-height 1.5. Â *[MR - UCD Audits â€¢ Department of Veterans Affairs (mural.co)¦https://app.mural.co/t/departmentofveteransaffairs9999/m/departmentofveteransaffairs9999/1685987646356/dde9adf5fd24b6e5d2431a77cb13ea15bf4b6cab]* *GIVEN:* *WHEN:* *THEN:* Â *Feature Flag Y/N ?* *DataDog AnalyticsÂ Y/N ?* *Manual Testing Y/N ?* Y Maruf *Automated Testing Y/N ?* *Accessibility Testing Y/N ?* *UCD Validation Y/N* Â *Acceptance Criteria:* AC1 Â Allergies details pageÂ has been updated with corrections noted AC2 AC3 AC4 Â *Links to UCD:* Figma Link: Other Design Notes: Â Â | Details page |  | To be prioritized
MHV-64547 | Audit: Update Vaccines Details page (TXT) | 1 |  | Audit: Update Vaccines Â Details page (TXT) 1-"Date entered:" text should be "Date received:" and located above "Location:" field. Â Â !vaccines detail page txt.PNG¦thumbnail! Â Â *[MR - UCD Audits â€¢ Department of Veterans Affairs (mural.co)¦https://app.mural.co/t/departmentofveteransaffairs9999/m/departmentofveteransaffairs9999/1685987646356/dde9adf5fd24b6e5d2431a77cb13ea15bf4b6cab]* *GIVEN:* *WHEN:* *THEN:* Â *Feature Flag Y/N ?* *DataDog AnalyticsÂ Y/N ?* *Manual Testing Y/N ?* Y-Sanjay *Automated Testing Y/N ?* *Accessibility Testing Y/N ?* *UCD Validation Y/N* Â *Acceptance Criteria:* AC1Â Details TXT has been updated with corrections noted AC2 AC3 AC4 Â *Links to UCD:* Figma Link: Other Design Notes: Â Â | Download BB | TXT File | To be prioritized
MHV-64545 | Audit: Update PDF and TXT for Vaccines | 1 |  | Audit: Update PDF and TXT for Vaccines Note:Â This is also noted in the Phase 1 bug spreadsheet Line item 26: Â ¦.txt file download of full vaccine list includes reaction field, which should no longer be included¦ 1-Remove VA Medical Record text. 2- Â Style of font should be regular PDF body text. 3- Â Content needs to be updated to match PDF text. 4- "Reaction:" field should be removed from vaccines. 5- Â "Reaction:" field should be removed from vaccines. 4th page Â Â Â Â !Vaccines PDF.PNG¦thumbnail! !Vaccines PDF 2.PNG¦thumbnail! Â Â *[MR - UCD Audits â€¢ Department of Veterans Affairs (mural.co)¦https://app.mural.co/t/departmentofveteransaffairs9999/m/departmentofveteransaffairs9999/1685987646356/dde9adf5fd24b6e5d2431a77cb13ea15bf4b6cab]* *GIVEN:* *WHEN:* *THEN:* Â *Feature Flag Y/N ?* *DataDog AnalyticsÂ Y/N ?* *Manual Testing Y/N ?* Y- Sanjay *Automated Testing Y/N ?* *Accessibility Testing Y/N ?* *UCD Validation Y/N* Â *Acceptance Criteria:* AC1 Â PDF has been updated with corrections noted AC2 AC3 AC4 Â *Links to UCD:* Figma Link: Other Design Notes: Â Â | Download BB | TXT File, PDF File | To be prioritized
MHV-64543 | Audit: Update PDF and TXT for Care Summary and Notes (Discharge Summary) | 1 |  | Audit: Update PDF and TXT for Care Summary and Notes (Discharge Summary) 1-Remove domain prefix (ticket for this already exists).Â 2- Please check logic for all 3 Discharge summary variations 3- Field should be "Date admitted:". Figma link for field logic: [https://www.figma.com/design/SGP1z2LejUWqDZyT61po5J/Medical-Records---Phase-1?node-id=11693-47825&t=4PgBuNEzwLgASRFY-1]Â 4-Field should be "Date discharged:". 5- Field order should be: Date admitted: Location: Date discharged: Discharged by: !discharge pdf.PNG¦thumbnail! !discharge pdf 2.PNG¦thumbnail! Â Â *[MR - UCD Audits â€¢ Department of Veterans Affairs (mural.co)¦https://app.mural.co/t/departmentofveteransaffairs9999/m/departmentofveteransaffairs9999/1685987646356/dde9adf5fd24b6e5d2431a77cb13ea15bf4b6cab]* *GIVEN:* *WHEN:* *THEN:* Â *Feature Flag Y/N ?* *DataDog AnalyticsÂ Y/N ?* *Manual Testing Y/N ?* Y Sanjay *Automated Testing Y/N ?* *Accessibility Testing Y/N ?* *UCD Validation Y/N* Â *Acceptance Criteria:* AC1 Â PDF and TXT have been updated with corrections noted AC2 AC3 AC4 Â *Links to UCD:* Figma Link: Other Design Notes: Â Â | Download BB | TXT File, PDF File | To be prioritized
MHV-64542 | Audit: Update PDF and TXT for Care Summary and Notes (Consult Note) | 1 |  | Audit: Update PDF and TXT for Care Summary and Notes (Consult Note) 1- Remove domain Prefix (if needed-another ticket exists for this) 2- Â Field should be "Date entered:". !Care Summary PDF.PNG¦thumbnail! Â Â *[MR - UCD Audits â€¢ Department of Veterans Affairs (mural.co)¦https://app.mural.co/t/departmentofveteransaffairs9999/m/departmentofveteransaffairs9999/1685987646356/dde9adf5fd24b6e5d2431a77cb13ea15bf4b6cab]* *GIVEN:* *WHEN:* *THEN:* Â *Feature Flag Y/N ?* *DataDog AnalyticsÂ Y/N ?* *Manual Testing Y/N ?* Y-Sanjay *Automated Testing Y/N ?* *Accessibility Testing Y/N ?* *UCD Validation Y/N* Â *Acceptance Criteria:* AC1 Â PDF and TXT has been updated with corrections noted AC2 AC3 AC4 Â *Links to UCD:* Figma Link: Other Design Notes: Â Â | Download BB | TXT File, PDF File | To be prioritized
MHV-64537 | Audit: Remove time from Pathology details page | 1 |  | Audit: Remove time from Pathology details page Â !image-2024-11-21-08-14-50-917.png! *[MR - UCD Audits â€¢ Department of Veterans Affairs (mural.co)¦https://app.mural.co/t/departmentofveteransaffairs9999/m/departmentofveteransaffairs9999/1685987646356/dde9adf5fd24b6e5d2431a77cb13ea15bf4b6cab]* *GIVEN:* *WHEN:* *THEN:* Â *Feature Flag Y/N ?* *DataDog AnalyticsÂ Y/N ?* *Manual Testing Y/N ?*Â *Automated Testing Y/N ?* *Accessibility Testing Y/N ?* *UCD Validation Y/N* Â *Acceptance Criteria:* AC1 Time has been removed from Pathology details page AC2 AC3 AC4 Â *Links to UCD:* Figma Link: Other Design Notes: Â Â | Details page |  | To be prioritized
MHV-63377 | Work for Staging Vistas - CVIX | 5 | muazzam.khan@va.gov | Work for Staging Vistas - CVIX Â *GIVEN:* *WHEN:* *THEN:* Â *Feature Flag Y/N ?* *DataDog AnalyticsÂ Y/N ?* *Manual Testing Y/N ?* Y-MarufÂ *Automated Testing Y/N ? N* *Accessibility Testing Y/N ? N* *UCD Validation Y/N N* Â *Acceptance Criteria:* AC1 Work has been completed for staging VistAs AC2 Test accounts with CVIX data available AC3 AC4 Â *Links to UCD:* Figma Link: N/A Other Design Notes: Â Â Â Â | Staging Test Environment |  | To be prioritized
MHV-63308 | HDR-work for Staging Vistas | 3 | muazzam.khan@va.gov | HDR Work for Staging Vistas Â *User Story: N/A* Â *Feature Flag Y/N ?*Â N/A *DataDog/Analytics Y/N ?*Â N/A *Manual Testing Y/N ?*Â Â N/A *Automated Testing Y/N ?*Â N/A *Accessibility Testing Y/N ?*Â N/A *UCD Validation Y/N*Â N/A *Acceptance Criteria:* AC1Â Â AC2Â Â AC3Â Â AC4 AC5 Â *Links to UCD:* Figma Link: User Flow: Mobile: Desktop: Other Design Notes: Â *Architectural Notes:* Always check for the latest designs in Figma | Staging Test Environment |  | To be prioritized
MHV-62905 | Read Me needs to be updated with plain language content | 1 | muazzam.khan@va.gov | Read Me needs to be updated with plain language content This is the readme.txt file that is located in the dicom zip file. +UCD will need to supply the new approved content+ Â *User Story:* As a Medical Images team, we want to have the ability to understand how to retrieve images and view images so that I can view my images in Medical Records. Â *Feature Flag Y/N ? N* *DataDog/Analytics Y/N ? N* *Manual Testing Y/N ?* Y-Maruf *Automated Testing Y/N ?* N *Accessibility Testing Y/N ?*Â Y *UCD Validation Y/N N* Â *Acceptance Criteria:* AC1 Readme.TXT file has been updated with new content for va.gov instructions AC2Â AC3Â AC4Â AC5 *Links to UCD:* Figma link: User Flow: Mobile: Desktop: Other Design Notes: *Architectural Notes:* Always check for the latest designs in Figma! | Imaging | DICOM Download | Need to plan the timing of this with stakeholders for when MHV is sunset.

## EPIC List
Issue key | Summary
MHV-64562 | Phase 1 MR Fast Follow
MHV-63374 | Tech Debt - PI18
MHV-63373 | Phase 0 Continuous Improvements - PI18
MHV-63372 | Radiology Images Download of JPEG to ZIP
MHV-62796 | Tech Debt - PI17
MHV-62584 | VIA to HDR - PITBD
MHV-62180 | MR-Detection and remediation of all silent errors
MHV-61970 | MR - UCD Research PI17
MHV-61969 | MR - UCD Design PI17
MHV-61966 | Phase 0 Continuous Improvements - PI17
MHV-61925 | Download Self Entered Health History
MHV-61924 | Download Medical Records
MHV-61663 | Download Continuity of Care Document (CCD)
MHV-61661 | Modify Endpoints (API Changes) - MR
MHV-61660 | HAPI FHIR to IRIS FHIR - PITBD
MHV-60064 | Comprehensive Test Data
MHV-59515 | OCTO Support PI?
MHV-58922 | Domain - Radiology Report - (FHIR)
MHV-56731 | Oracle Health - Manage Data Updates/Changes
MHV-50888 | Oracle Health - EKG (TBD)
MHV-50887 | Oracle Health - Care Summaries & Notes
MHV-50886 | Oracle Health - Health Conditions
MHV-50885 | Oracle Health - Vitals
MHV-50884 | Oracle Health - Labs Radiology Images
MHV-50883 | Oracle Health - Labs Radiology Reports
MHV-50882 | Oracle Health - Labs Pathology
MHV-50881 | Oracle Health - Labs Microbiology
MHV-50880 | Oracle Health - Labs Chem/Hem
MHV-50879 | Oracle Health - Vaccines
MHV-50868 | Oracle Health - Allergies
MHV-50867 | Oracle Health - Data Mapping & Analysis
MHV-50866 | Oracle Health - Authentication HTTPS OAuth 2.0
MHV-49230 | Prepare for Phase 1
MHV-48774 | Backend FHIR API improvements - PI(TBD)
MHV-48146 | Domain - EKG - Backlog
MHV-48112 | Domain - Radiology Images Initial Experience
MHV-41296 | MR Future Ideas